## Login & Task Visu
Project Name |  | SCT Task Management System | TC Start Date | 2022-03-11 | TC Execution Start Date | 2022-03-11 | TEST CASE SUMMARY
Module Name |  | Login, Task visu | TC End Date | 2022-03-12 | TC Execution End Date | 2022-03-12 | PASS | 2
|  |  | Test Case Developed By | Ibne Sayad | Browser (tested) | Yes | FAIL | 5
Developer Name (TL) |  | Null | Test Case Reviewed By | Ibne Sayad | Performance (tested) | No | WARNING | 5
Test Executed by |  | Ibne Sayad |  |  |  |  | TOTAL | 12
Test Case ID/Name | Test Case Description | Step Name | Test Data | Step Description | Expected Result | Actual | Status | Remarks
LP 001 | Login page Language change | Change language | Click | Click on Language Dropdown | Language will change to another | Language changing but the level should be in capital letter | Warning | Screenshot
LP 002 | Input filed's level test | Check the levels of the fields | Check | Check the level | All the levels should be correct splled and properly visualized . | > "Login" level should be little bold and larger font. > Remove space between "User" & "Name". It should be Username. | Fail | Screenshot
LP 003 | Check wrong credential's alert | Provide wrong input | Username = fghr Password= erjorge | Fill username Fill Password | Sould give wrong credential alert | > Alert showing but not visible properly. -> The font size should little biger and color should visible clearly. | Warning | Screenshot
LP 004 | check with wrong password | Provide wrong password | Username = administrator Password= sct-brixen Extra space added after original password | Provide user name Provide password | Becasuse of extra spaces added so llogin can't occured. | -> Even if two extra space been added after the original password. It's still loging in | Fail | Screenshot
TV 005 | Header UI test | Check header UI | Check the visibility | Check all the UI | All should visible properly | The header menu it not visible properly. The color combinition is not so good. And logo image is invalid. | Warning | Screenshot
TV 006 | Create Task | Provide all the info | Provide data for all the fields | Add Task name, Team, Date, Person, Contact Person, Resonsible person, Priority Color, Progress, & Description | All information should updated | All the information updated properly & required filed is action as required | Pass | Passed
TV 007 | Take a view about the task Description | View the task description | View | See task description | should be viewed properly | Data is showing but visibility not so good. It should be viewed properly. | Warning | Screenshot
TV 008 | Search by task name & responsible | Provide task name & responsible name | Task Name: Task name Responsible: Admin | > Task name > Responsible | Data are coming | > Expected output is coming but there are some modifications. 1. There should be a place holder for searching. 2. After providing the data the cross icon is not visible properly. | Warning | Screenshot
TV 009 | Take action with download button | Click on the download button | Click | >Click | > File should download | > No file's are downloading | Fail | Screenshot
TV 010 | Update the task | Update name and other fields | Name: Task name has been updated | > Update name of the task | > Name should be updated with other updated info | > All are updating properly. | Pass | Screenshot
TV 011 | Add image to the text area | Go to the text area and add a new image | Image link Alt Test Width Height | Update the provided information | > Image should previewed to the text area' | > Image is not previewing . | Fail | Screenshot
TV 012 | Check the responsive issue | Convert the screen to the responsive mode and test the contents | Turn on the responsive mode. | Turn on the responsive mode. | > All the contents should be in proper alligned. | > Contents are not correct alligned. | Fail | Screenshot
Pass
Fail
Warning